# Terms of reference 
and technical Specifications

- General information

| # Assignment name | # Improving path for privatization of sanctioned assets |
| --- | --- |
| # Beneficiary | # State Property Fund of Ukraine |
| # Country | Ukraine |
| # Total estimated number of days | # 150 |

- Context and justification of the need

EF Project “Assistance to the State Property Fund of Ukraine” is aiming to support the improvement of the management of the state property in Ukraine, to contribute to the alignment of Ukrainian practices with EU standards and best practices and enhance the country’s economic resilience. More specifically, the project is seeking to:

- Assist the Fund in the steering and implementation of the corporate governance reform;

- Support the development of an effective mechanisms for timely detection and minimization of risks related to the state property management (through automation of the process via the development of an Early Response System);

- Support the Fund in the management – and ultimately privatization – of sanctioned assets transferred to the SPFU through decision of the High Anti-Corruption Court;

- Facilitate the leasing of agricultural lands managed by the SPFU, through the development and operationalization of a landbank system.

The Project is composed of four Components as follows:

Component 1: Enhancing SPFU capacity to steer and implement the reform of the management of state property

Component 2. Support for automation of corporate governance of state-owned enterprises: development of the Early Response System (ERS)

# Component 3: Support to the management and liquidation of sanctioned assets

# Component 4: Support to the registration of public land plots and their transfer to the Land Bank Operator

- Objectives and desired results

  - General objective

The objective of the assignment is identify legal issues hindering the participation of foreign investors in auction for sanctioned assets and propose suggestions to overcome them.

  - Specific objectives

- Identify the main risks for foreign investors in participation and purchase of assets coming from sanctions;

- Identify the main legal provisions, international practices & relevant experiences from other countries to use in order to put in distance and/or minimize those risks;

- Draft legal proposals to integrate into the Ukrainian legislation

  - Anticipated results

Presentation of legal proposals to be integrated in the legislation as to remove barriers & add incentives for the participation to auctions for sanctioned assets by foreign investors.

- Description of the assignment

  - Planned activities

Assignment preparation

- Prepare and provide the following documents :

  - a workplan for carrying out the whole assignment & related calendar;

  - a list of expertise needed,

  - list of partners & stakeholders to be associated to the assignment,

- Present the plan to carry out the assignment to Expertise France

Phase I: Risk assessment

- Identify the main risks faced by foreign investors that would purchase assets whose property rights have been transferred following sanctions.

  - On the legal security of the property rights transfer;

  - On the threat of litigation in foreign courts;

  - On the likelihood of assets being located abroad being seized during foreign litigation procedures;

  - On any measures that could be taken by the former owner against the new owner in Ukraine or any foreign jurisdiction.

- Gather and include feedback from potential foreign investors, such as investment banks and/or former participants in privatization sales in Central & Eastern Europe.

- Present the findings in a risk assessment report.

Phase II: Gap analysis

- Review the existing legislation based on the main risks identified;

- Review the European and Member States legislation as to identify good practices & recommendations on such cases;

- Prepare a report on the main barriers & gaps within Ukrainian & regional legislation.

Phase III: Drafting recommendations

- Identify of relevant experiences & practices based on foreign experiences of privatization of such large scales assets by foreign investors who have stakes & assets located in foreign countries.

- Gather suggestions & recommendations from potential investors & foreign investment banks;

- Draft amendments & legislative changes to include these findings and mechanisms within the Ukrainian legislation;

- Conduct interviews, on/off discussions with all range of stakeholders to ensure wide spread support for the recommendations & mechanisms developed.

Post-assignment follow-up: Presentation of the main findings during dedicated high-level event

- Organize an in-person restitution & advocacy event – format to be agreed with Expertise France.

  - Anticipated deliverables

| Deliverables | End date |
| --- | --- |
| - Risk assessment report | T0 + 1 month |
| - Gap analysis report | T0 + 1,5 months |
| - Suggestions & proposals report | T0 + 2,5 months |
| - Restitution event | T0 + 3 months |

  - Coordination

The service provider shall designate a single contact person for project implementation purposes.

Clement Lapointe will be the service provider’s sole contact person for Expertise France.

E-mail: clement.lapointe@expertisefrance.fr

A launch meeting shall be held 5 days after the contract award has been notified.

Close collaboration must take place with Clement Lapointe, Team Leader for Expertise France from assignment preparation right up to completion. Furthermore, regular exchanges must take place on assignment progress and any difficulties that may be encountered.

- Place, duration and terms of performance

  - Implementation period: up to 4 months

  - Start date: 01/12/2025

  - End date: 01/03/2025

  - Schedule/program:

The provisional program for assignment implementation is as follows:

| Activity | Place | Period | Estimated duration (man/days) : |
| --- | --- | --- | --- |
| Assignment preparation | Kyiv | November | 5 |
| Risk assessment – Phase 1 | Kyiv | December | 40 |
| Gap analysis – phase 2 | Kyiv | January | 45 |
| Recommendation development – phase 3 | Kyiv | February | 50 |
| Finding presentation – post assignement | Kyiv | February | 10 |
| Total |  |  | 150 |

- Required expertise and profile

  - Profile of the designated expert(s) responsible for contract execution

- Strong knowledge of commercial, criminal, civil & property, tax legislations; regulatory framework of state assets management, sanctions framework.

- Strong knowledge of international sanctions regimes.

- Previous experience in policy making and drafting of legal documents.

- Good knowledge of national and international case law regarding the application of sanctions.

- More than 4 past references on submission of legal opinion and analysis on sanction cases & regime.

- Strong analytical skills.

- Language: Fluency in Ukrainian and English.

- Monitoring-evaluation

Performance indicators

| Deliverables | Immediate effects | Intermediate effects | Verification sources |
| --- | --- | --- | --- |
| Recommendation for changes in the legislations | Submission of amendments and draft law for registration in Verkhovna Rada |  | Verkhovna Rada website |